## Schedule
WEEK OF | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
2025-05-12 | PT-Final Review
2025-05-19
2025-05-26
2025-06-02 |  |  | CA-WB1
2025-06-09
2025-06-16 |  |  |  | TR-E1+E2 [ML]
NL-E1 WB2
2025-06-23 |  |  |  | CA-WB2
2025-06-30 | CA-E1 [ML] - 11am PST | TR-E3 [ML] - 10am PST
2025-07-07 | JP-WB2 |  | KO-WB1 - 8am PST | TR-E4 [PB] - 10am PST
CA-E1+E2 - 10am PST
2025-07-14 | KO/JP font updates |  | KO-E1 Test - 11am PT | TR-E5 [PB/ML?] - 11am PST
| NL-E1 |  |  |  | CA-E3 - 8am PST
2025-07-21 | KO/JP font updates |  | KO-E1 | TR-E6 [ML + PB] - 10am PST
2025-07-28 | KO/JP font updates |  |  | TR-E7 [PB] - 10am PST
NL-E2
2025-08-04 | KO/JP font updates |  | KO-E2 | TR-E8+E9 - TBD
2025-08-11 | KO/JP font updates |  | KO-E3 | TR-E10 - TBD
2025-08-18 | KO/JP font updates | KO-E4 | CA-E4-E5? - 8am PST [ML] | TR-Polishing - TBD
2025-08-25 | KO/JP font updates | KO-E5 | CA-E5 - 8am PST [ML]
2025-09-01 | KO/JP font updates | CA-E6
| Create Show Ready vs. In-Development branches Show Ready: PT playthrough TR playthrough EN playthrough In-Dev: NL, CA, KO, JP |  | KO-E6 |  |  |  | EN-PERFORMANCE
2025-09-08 | KO/JP font updates | CA-E7 + E8 | KO-E7 |  |  | FR-PERFORMANCE
2025-09-15 |  |  | KO-E8 + E9 | TR-Final Review |  | TR-PREMIERE | TR-PREMIERE
2025-09-22 |  | PT-Stability Playthrough |  |  |  | PT-PREMIERE | EN-PERFORMANCE
2025-09-29 |  |  | KO-E10 + 0 |  |  | EN-PERFORMANCE
2025-10-06 |  | CA-E9 + E10
2025-10-13 |  | CA-E0 and animation checks
2025-10-20 | [6 empty] | EN-PERFORMANCE
2025-10-27 |  |  | CA-Final Review |  |  | CA-PREMIERE | CA-PREMIERE
2025-11-03 |  |  | KO-Final review |  |  | KO-PREMIERE | KO-PREMIERE
2025-11-10
2025-11-17 | MERGE CA AND KO TO MAIN BRANCH Leave NL + JP
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26
2026-02-02
2026-02-09
2026-02-16
2026-02-23
2026-03-02
2026-03-09
2026-03-16
2026-03-23
2026-03-30
2026-04-06
2026-04-13
2026-04-20
2026-04-27
2026-05-04
2026-05-11 | [5 empty] | NL-PREMIERE | NL-PREMIERE
Formulas:
WEEK OF = [WEEK OF, row below]-7
WEEK OF = [WEEK OF, row above]+7

## TR
EMRE | Action | Translated | Notes
All | World Building Meeting 1: Names, Tone, Humour | x
All | World Building Meeting 2: Make Decisions on Names, etc. (They can change!) | x
Translator | Test translation of E1 Stable 1F + E1 Farm | x
All | Review Test Translation | x
Translator | E0
All | Review
Translator | E1 | x
All | Review | x
Translator | E2 | x
All | Review | x
Translator | E3 | x
All | Review | x
Translator | E4 | x
All | Review | x
Translator | E5 (both) | x
All | Review | x
Translator | E6
All | Review
Translator | E7
All | Review
Translator | E8
All | Review
Translator | E9
All | Review
Translator | E10
All | Review
Patrick | Redraw/Animate all NonCSV elements |  | See here for list: 11_asses.masses_NonCSVBasedTranslations
Patrick | E10 Words; Manual input, add all targeted GameObject, reposition all respawn colliders
Patrick | Add new Sprites/Animations to GameObjects
Milton | Export Well video
Patrick + Milton | Final full playthrough with all translated elements before premiere
PLAYTHROUGH NOTES
Hyphens for Smart list
Revisit names to discuss meanings: particularly Bad Ass, Sick Ass, and Human names
Set up Foal name to have Esek
Return to song of ascension phonemes: AA II, AH IH, AAH, IIH, A'H, 'IIH — update video after
Add S-with cedilla to YOLDAS -- Dos font
Revisit Farm House Radio (milton broke it early)
Make all ÖHÖ captials and ensure that single vs. double is correct
Bumpkin Sign
Fannyside Flour sign
Check alignment Pleasure:
Did not test Bad Ass Rescue
Update song of ascension text in E2 B1
Need to Translate E2 ButteHouse
EY - Change name of attacks in Butte Battle
Review attacks to be more like Pokemon in E2 battles
Capitalize the attacks in E2 battles
Can we make a really long word for the song of ascension? |  | Eşekleştiremeyeceklerimizdenmişçesine
What is the Machine ending?
Update e1 and e2 names for characters in dialogues
Update to Uncle Kaba to Maternal uncle: Kaba Dayı
PB Localize Zoo in Newspaper: hayvanat bahçesi
ömür / kömür renaming Cole Butte?
Be an Esek not a Ezik
Can we think of a better acronym for Humans Are the Worst
Acımasız İnsanlara Acıma
Think about where Tesekkuler (?) fits at the very end of the game in the Epilogue, because it's a very beautiful word within donkey in

## CA
MARC | Action | Translated | Notes
All | World Building Meeting 1: Names, Tone, Humour | x
All | World Building Meeting 2: Make Decisions on Names, etc. (They can change!) | x
Translator | Test translation of E1 Stable 1F + E1 Farm | x
All | Review Test Translation | x
Translator | E0
All | Review
Translator | E1 | x
All | Review | x
Translator | E2 | x
All | Review | x
Translator | E3 | x
All | Review | x
Translator | E4
All | Review
Translator | E5 (both)
All | Review
Translator | E6
All | Review
Translator | E7
All | Review
Translator | E8
All | Review
Translator | E9
All | Review
Translator | E10
All | Review
Patrick | Redraw/Animate all NonCSV elements |  | See here for list: 11_asses.masses_NonCSVBasedTranslations
Patrick | E10 Words; Manual input, add all targeted GameObject, reposition all respawn colliders
Patrick | Add new Sprites/Animations to GameObjects
Milton | Export Well video
Patrick + Milton | Final full playthrough with all translated elements before premiere
PLAYTHROUGH NOTES
Will meet on June 30
Need to add Punt Volat to all fonts
Create Unicode address for it in foal name select script; What other letters are required? ç?
Morale check capitalization
Other versions of "cartell" for sign?
c, p, t for stuttering
Check for bad ass to be complete before night called (more complicated)
Rucorn
Radio in E1 Farm House not checked
Look at English battle text to standardize
Utilisa + CAPS
THIRSTY: Changed Thirsty's region from Northern to Southern with richer vocabulary, losing some age, but accent is strong so it sounds countryside and out of touch with the world
NICE ASS: Nice Ass is still not present, but playing with Gen Z (maybe uses a lot of English language), trying to stay away from caricature
PRONOUNS: L'Expertase vs La Expertase and it depends on where the stress of the vowels; Marc suggests that we keep La even if it's wrong.
Asses' Well: Flagged // Sant Hilasi
Normal for rocks
Paner = butt and bread
Big City Circus sprite is not updated in the newspaper
- Missing UI sprite for current language for Newspaper_CircusTitle
* Image_MECHA
* Image_RECEIPT
Why are some things struck through on the sheet 11?
Fix Prophet sign and change it to -453 for Ase
Pick font for rhythm game 3D language

## KO
JOON | Action | Translated | Notes
All | World Building Meeting 1: Names, Tone, Humour | x
All | World Building Meeting 2: Make Decisions on Names, etc. (They can change!)
Translator | Test translation of E1 Stable 1F + E1 Farm | x
All | Review Test Translation | x
Translator | E0
All | Review
Translator | E1
All | Review
Translator | E2
All | Review
Translator | E3
All | Review
Translator | E4
All | Review
Translator | E5 (both)
All | Review
Translator | E6
All | Review
Translator | E7
All | Review |  | See here for list: 11_asses.masses_NonCSVBasedTranslations
Translator | E8
All | Review
Translator | E9
All | Review
Translator | E10
All | Review
Patrick | Redraw/Animate all NonCSV elements
Patrick | E10 Words; Manual input, add all targeted GameObject, reposition all respawn colliders
Patrick | Add new Sprites/Animations to GameObjects
Milton | Export Well video
Patrick + Milton | Final full playthrough with all translated elements before premiere
PLAYTHROUGH NOTES
Priority: | Check with Joon about input standards for korean (manual commit etc.)
Remember to add the not allowed name check: if (player.text + "Korean Donkey" == notAllowedNamesKO[i])
https://www.loc.gov/marc/specifications/specchareacc/KoreanHangul.html
https://jrgraphix.net/research/unicode_blocks.php
Very low tolerance on drug use
Is there a legal consequence of representing drug use in media?
Should all character names be four syllables?
Watch for missing periods
Vertical letter with notch is a bit hard to read
Size 50 with line weight of 1pt; 3 lines per block (redo the sizing reference)
Signage in E1 was JP not KO—is the error in the signage sprite order or in the PSD?

## NL
TOM | Action | Translated | Notes
All | World Building Meeting 1: Names, Tone, Humour | x
All | World Building Meeting 2: Make Decisions on Names, etc. (They can change!)
Translator | Test translation of E1 Stable 1F + E1 Farm | x
All | Review Test Translation
Translator | E0
All | Review
Translator | E1
All | Review
Translator | E2
All | Review
Translator | E3
All | Review
Translator | E4
All | Review
Translator | E5 (both)
All | Review
Translator | E6
All | Review
Translator | E7
All | Review
Translator | E8
All | Review
Translator | E9
All | Review
Translator | E10
All | Review
Patrick | Redraw/Animate all NonCSV elements |  | See here for list: 11_asses.masses_NonCSVBasedTranslations
Patrick | E10 Words; Manual input, add all targeted GameObject, reposition all respawn colliders
Patrick | Add new Sprites/Animations to GameObjects
Milton | Export Well video
Patrick + Milton | Final full playthrough with all translated elements before premiere
PLAYTHROUGH NOTES
Fix apostraphe at start of sentence
Full pass on capitalization of core concepts (See Localization Manual)
Pass on dialect of Thirsty aim for 80%?
Poep jokes -- Poepsimpel
Quite few bodily reference puns/wordplays coming: ears, hoofs, teeth, shit, maw Some additional to consider: tails, hoef, hides
Return to the Ass Power slogan:
Mecha City >> Mechalen ¦¦ explore words around mechanization, technology, machines, etc. to appear near it in the text
Stront (shit) / Strontium (chemical element)
Achterwerk >> let's see how far we can make Werk go

## JP
KYLE | Action | Translated | Notes
All | World Building Meeting 1: Names, Tone, Humour | x
All | World Building Meeting 2: Make Decisions on Names, etc. (They can change!)
Translator | Test translation of E1 Stable 1F + E1 Farm
All | Review Test Translation
Translator | E0
All | Review
Translator | E1
All | Review
Translator | E2
All | Review
Translator | E3
All | Review
Translator | E4
All | Review
Translator | E5 (both)
All | Review
Translator | E6
All | Review
Translator | E7
All | Review
Translator | E8
All | Review
Translator | E9
All | Review
Translator | E10
All | Review
Patrick | Redraw/Animate all NonCSV elements
Patrick | E10 Words; Manual input, add all targeted GameObject, reposition all respawn colliders |  | See here for list: 11_asses.masses_NonCSVBasedTranslations
Patrick | Add new Sprites/Animations to GameObjects
Milton | Export Well video
Patrick + Milton | Final full playthrough with all translated elements before premiere
PLAYTHROUGH NOTES

## Template
Translator: #### | Action | Translated | Notes
All | World Building Meeting 1: Names, Tone, Humour
All | World Building Meeting 2: Make Decisions on Names, etc. (They can change!)
Translator | Test translation of E1 Stable 1F + E1 Farm
All | Review Test Translation
Translator | E0
All | Review
Translator | E1
All | Review
Translator | E2
All | Review
Translator | E3
All | Review
Translator | E4
All | Review
Translator | E5 (both)
All | Review
Translator | E6
All | Review
Translator | E7
All | Review
Translator | E8
All | Review
Translator | E9
All | Review
Translator | E10
All | Review
Patrick | Redraw/Animate all NonCSV elements
Patrick | E10 Words; Manual input, add all targeted GameObject, reposition all respawn colliders
Patrick | Add new Sprites/Animations to GameObjects
Milton | Export Well video
Patrick + Milton | Final full playthrough with all translated elements before premiere
PLAYTHROUGH NOTES